## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | taskID | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | taskID | Total bestCase ManHours | Total expected ManHours | Total worstCase ManHours
A | Describe product |  | 8 | 12 | 16 | A | 1 | 0 | 0 | 1 | 1 | A | 24 | 36 | 48
B | Develop marketing strategy |  | 24 | 40 | 60 | B | 1 | 0 | 0 | 1 | 0 | B | 48 | 80 | 120
C | Design brochure | A | 16 | 24 | 32 | C | 0 | 3 | 0 | 0 | 0 | C | 48 | 72 | 96
D | Develop product prototype |  |  |  |  | D | [5 empty] | D
D1 | Requirements analysis | A | 40 | 60 | 80 | D1 | 1 | 0 | 3 | 0 | 0 | D1 | 160 | 240 | 320
D2 | Software design | D1 | 60 | 90 | 120 | D2 | 0 | 3 | 3 | 0 | 0 | D2 | 360 | 540 | 720
D3 | System design | D1 | 60 | 90 | 120 | D3 | 0 | 0 | 3 | 0 | 1 | D3 | 240 | 360 | 480
D4 | Coding | D2, D3 | 120 | 200 | 280 | D4 | 0 | 3 | 3 | 0 | 0 | D4 | 720 | 1200 | 1680
D5 | Write documentation | D4 | 40 | 60 | 80 | D5 | 0 | 3 | 3 | 0 | 0 | D5 | 240 | 360 | 480
D6 | Unit testing | D4 | 40 | 80 | 120 | D6 | 0 | 3 | 3 | 0 | 0 | D6 | 240 | 480 | 720
D7 | System testing | D6 | 40 | 80 | 120 | D7 | 0 | 0 | 3 | 0 | 1 | D7 | 160 | 320 | 480
D8 | Package deliverables | D5, D7 | 24 | 40 | 56 | D8 | 0 | 0 | 3 | 0 | 1 | D8 | 96 | 160 | 224
E | Survey potential market | B, C | 40 | 60 | 80 | E | 0 | 0 | 0 | 2 | 0 | E | 80 | 120 | 160
F | Develop pricing plan | D8, E | 16 | 24 | 32 | F | 1 | 0 | 0 | 2 | 0 | F | 48 | 72 | 96
G | Develop implementation plan | A, D8 | 20 | 30 | 40 | G | 1 | 0 | 0 | 0 | 0 | G | 20 | 30 | 40
H | Write client proposal | F, G | 8 | 12 | 16 | H | 1 | 0 | 0 | 0 | 0 | H | 8 | 12 | 16